## L版本BP
Priority | Blueprint | Design | Delivery | Assignee | Milestone | 备注
High | convergence-check-workflow | Approved | Implemented | Sirushti Murugesan | 5.0.0 | 查询convergence资源状态，并进行处理 - Kick off workflow from stack update - Implement skeleton check_resource function that propagates the traversal through the workflow using SyncPoints - Notify the stack of the result when done
High | convergence-prepare-traversal | Approved | Implemented | Rakesh H S | 5.0.0 | 为遍历栈加载和产生依赖图 - Load all extant Resources from the DB - Determine which are up to date - Create new Resources where necessary - Calculate the traversal graph - Roll back (e.g. delete newly-created resources) if we lose a race to be the next update (i.e. fail to update the Stack atomically in the DB)
High | convergence-resource-operations | Approved | Implemented | Kanagaraj Manickam | 5.0.0 | 执行convergence资源创建、更新、删除 - Ideally just a wrapper around modified Resource.(create¦update¦delete) that starts them using a TaskRunner - May need customised implementations if the same code can't be made to work for both legacy- and convergence-style stacks - If we're trying to UPDATE a resource that is DELETE_IN_PROGRESS, just create a replacement
High | convergence-resource-replacement | Approved | Implemented | Angus Salkeld | 5.0.0 | 创建DB替代入口，并且链接到已经存在的资源 - Upon UpdateReplace, create a replacement entry in the DB and link it to the existing resource
High | convergence-rollback | Approved | Implemented | Anant Patil | 5.0.0 | convergence回滚处理 - Just an update with the previous template - Need to ensure that old templates are kept around so long as they are still referenced, and deleted when they are not
High | nested-validation | Approved | Implemented | Jay Dobies | 5.0.0 | 允许嵌套资源的验证和检验 Currently, there's no way to recursively validate all nested templates other than doing a stack-create and waiting for it to fail. Additionally, there's no way to inspect the interfaces exposed by nested template, e.g those accessible via parameter_defaults. Adding more comprehensive support for pre-create validation (e.g heat template-validate) will allow solving both of these issues.
High | resource-group-batching | Approved | Implemented | Oleksii Chuprykov | 5.0.0 | 在ResourceGroup中增加批量create Add such functionality to resource group: rolling_update, similary as in autoscaling_group rolling_create for creating resources in batches, especially necessary for deployment of large stacks.
High | rich-network-prop | Approved | Implemented | Sergey Kraynev | 5.0.0 | 丰富os:nova:server类型network属性 Allowing port and floating IP association properties to be specified within a OS::Nova::Server works around issues with nova port management, provides users with a simpler way of implementing a common pattern, and allows more templates to be neutron/nova-networking agnostic.
Medium | add-manila-resources | Approved | Implemented | Tetiana Lashchova | 5.0.0 | 增加manila相关资源类型 Since Manila has been an OpenStack incubated project， Heat should add relevant resources supports for Manila, like shared volume, shared network and so on.
Medium | constraint-validation-cache | Approved | Implemented | Kairat Kushaev | 5.0.0 | 缓存约束检查结果 The specification describes changes in validation of property constaints. It allows to reduce number of API requests to other components.
Medium | convergence-concurrent-workflow | Approved | Implemented | Angus Salkeld | 5.0.0 | 处理convergence并发情况 - If a locked resource is encountered and the lock can't be broken, stop processing - Upon unlocking a resource, check to see that the current traversal is still in effect and trigger the latest traversal of the node if appropriate
Medium | convergence-lightweight-stack | Approved | Implemented | Sirushti Murugesan | 5.0.0 | convergence加载轻量级stack This patch allows creating lightweight stacks using a cache provided which will never query the database and only depend on the template and the cache provided. Function resolutions will now happen by querying the values in the cache provided if it exists else None is returned. The resultant lightweight stack will effectively be the stack attributes loaded from the database and it's raw template with the dependent resource's functions resolved which will serve as the input for individual resource objects that will be worked upon.
Medium | convergence-simulator-tests | Approved | Implemented | Ishant Tyagi | 5.0.0 | convergence增加单元测试用例
Medium | encrypt-hidden-parameters | Approved | Implemented | Vijendar Komalla | 5.0.0 | 把属性为hidden的parameter加密 Encrypt template parameters that were marked as hidden before storing them in database.
Medium | get-attr-all-attributes | Approved | Implemented | Peter Razumovsky | 5.0.0 | heat可以获取资源的所有属性 Add new special form of { get_attr: [resource_name] } with no extra arguments which will return dict of all resource's attributes.
Medium | heat-designate-resource | Approved | Implemented | Kanagaraj Manickam | 5.0.0 | 新增Designate资源 Resource plugin for Designate service
Medium | heat-resource-type-search | Approved | Implemented | Kanagaraj Manickam | 5.0.0 | heat支持resource-type搜索 Affected Service REST API: /v1/​{tenant_id}​/resource_types?filter=<query parameters> Affected Heat CLI: (only shown the new parameters here) `heat resource-type-list [-f <KEY1=VALUE1;KEY2=VALUE2...>]
Medium | keystone-based-resource-availabi... | Approved | Implemented | Kanagaraj Manickam | 5.0.0 | 只列出可用的resouce-type Updates engine resource_type listing to consider the availability of resource based on service deployed and configured in keystone
Medium | mistral-resources-for-heat | Approved | Implemented | Peter Razumovsky | 5.0.0 | heat增加mistral资源类型 | Mistral是mirantis公司为openstack开发的工作流组件，提供WorkFlow as a service。 典型的用户用例包括云平台的任务计划服务（Cloud Cron），任务调度（Task Scheduling）， 复杂的运行时间长的业务流程服务。目前项目还在开始阶段。对应的是AWS的SWS（Simple WorkFlow Service）。
Medium | noop-resource | Approved | Implemented | Steven Hardy | 5.0.0 | 增加OS::Heat::None类型 Add a "None" resource, intended to simplify mapping resource_registry entries to an implemention which always passes, but does nothing, this is useful when you want to disable a particular resource via the resource_registry.
Medium | software-config-zaqar | Approved | Implemented | Thomas Herve | 5.0.0 | 增加zaqar相关资源类型 Zaqar provides a simple messaging service which allows heat and orchestrated services to efficiently communicate with each other, which make it ideal for software-config metadata distribution and signaling
Medium | str-split | Approved | Implemented | Steven Hardy | 5.0.0 | From HOT 2014-10-16 we no longer support the AWS compatible Fn::Split intrinsic function in HOT templates, which means there's no way to split a string into a list of components by delimiter. Adds a new intrinsic function to split strings into lists, and optionally return a specific list item by index (similar to get_attr/get_param path based attributes).
Medium | support-actions-for-remote-stack | Approved | Implemented | huangtianhua | 5.0.0 | 支持远程stack操作 After heat supports to create stack across multiple regions, some actions such stack-snapshot and stack-restore and so on should be supported for remote stacks.
Medium | template-function-list | Approved | Implemented | Oleksii Chuprykov | 5.0.0 | template-function-list template-version-list
Medium | trust-alarm-urls | Approved | Implemented | Thomas Herve | 5.0.0 | Provide a signal URL attribute for alarms This patch adds a new attribute to scaling policies allowing it to be called by the ceilometer service user using trusts on alarming.
Medium | update-dry-run | Approved | Implemented | Jason Dunsmore | 5.0.0 | 增加heat update --dry-run以便查询update所做的修改 Performing a stack update is a potentially destructive operation - resources may need to be replaced. The user can get a reasonable idea by scouring the documentation of each property that is changing, but it's a tedious and error-prone process. The user needs to be able to do "heat update --dry-run" or something similar to obtain a list of the changes that will be made for a given update.
Low | add-cinder-backup-constraint | Approved | Implemented | huangtianhua | 5.0.0 | Add cinder backup constraint Add backup custom constraint and apply it to related resource property.
Low | add-type-in-attributes-schema | Approved | Implemented | Ishant Tyagi | 5.0.0 | 给get_attr返回值增加type Currently there is no way to find out what is the type of attribute returned by the get_attr function. This makes it difficult for the template authors to figure out what type of value will be returned. Indexing and Mapping on the attributes also becomes a issue without the knowledge of the attribute type.
Low | barbican-resources | Approved | Implemented | andersonvom | 5.0.0 | Add Barbican resources OS:Barbican:Order OS:Barbican:Secret OS:Barbican:Verification
Low | guru-meditation-report | Approved | Implemented | huangtianhua | 5.0.0 | Add Guru Meditation Report Functionality to Heat Nova contains a mechanism whereby developers and system administrators can generate a report about the state of a running Nova executable. This report is called a Guru Meditation Report (GMR for short).
Low | keystone-resource-service-endpoint | Approved | Implemented | Kanagaraj Manickam | 5.0.0 | Heat Resource plugin for Keystone Service and Endpoint
Low | no-downward-sql-migrations | Approved | Implemented | Tetiana Lashchova | 5.0.0 | Eliminate SQL Schema Downgrades.
Low | server-snapshot-policy | Approved | Implemented | Thomas Herve | 5.0.0 | Support snapshot deletion policy in Server We only support the Snapshot DeletionPolicy in volumes, we should support if for servers too using image creation.
Low | stack-tags | Approved | Implemented | Jason Dunsmore | 5.0.0 | Stack tags Heat may be used by cloud providers for behind-the-scenes orchestration. For example, creation of a Nova server might include, by default, creation & configuration of a network, subnet, port, and security group. To improve user experience, stacks used for behind-the-scenes orchestration should be hidden. This feature will allow creation of hidden stacks and an option to show hidden stacks as part of stack-list.
Low | support-monasca-alarm-notification | Approved | Implemented | Kanagaraj Manickam | 5.0.0 | Monasca provides monitoring-as-a-service. To support the operation of Monasca resources in Heat, the following resources needs to be implemented: - Alarm - Notification Besides, Monasca client should be implemented.
Low | support-to-generate-hot-templates | Approved | Implemented | huangtianhua | 5.0.0 | support to generate hot templates for resource-type template Now, heat only supports to return the 'HeatTemplateFormatVersion' template of resources, will be good to support other template versions especially hot template, so this bp will support user to specify the template version while generating resource template.
Low | template-version-list | Approved | Implemented | Oleksii Chuprykov | 5.0.0 | >heat template-version-list Possible output: heat_template_version.2013-05-23 heat_template_version.2014-10-16 heat_template_version.2015-04-30 HeatTemplateFormatVersion.2012-12-12 AWSTemplateFormatVersion.2010-09-09
Low | test-resource-for-functional-tests | Approved | Implemented | Anant Patil | 5.0.0 | 模拟资源创建失败和更新方便测试 Functional tests requires resources with finer control over their behavior. For example, tests require a resource to emulate failure to test rollback, or emulate update-in-place to test certain scenarios of stack update.
Low | support-cinder-volume-type-acces... | New | Implemented | huangtianhua | 5.0.0 | Support add project access and remove project access for private cinder volume type.
Undefined | cinder-volume-encryption | Approved | Implemented | Rakesh H S | 5.0.0 | 支持cinder加密 Cinder provide encrypted volume type for creating the encrypted volume.
Undefined | enhance-property-constraints | Drafting | Implemented | Ethan Lynn | 5.0.0 | 对属性进行有效性检查